## Sheet1
Start | S_Dependency | End | E_Dependency | LineTitle | Color | Annotation | ResourceAllocation | NOTES
| <> |  | <> | \textbf{Programme \& consortia management}
2020-10-01 | <> | 2020-10-08 | =A3+7 | Research development group meeting | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)}
2021-04-01 | =edate(A3,6) | 2021-04-08 | =A4+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)}
2021-10-01 | =edate(A4,6) | 2021-10-08 | =A5+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)}
2022-04-01 | =edate(A5,6) | 2022-04-08 | =A6+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)}
2022-10-01 | =edate(A6,6) | 2022-10-08 | =A7+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)}
2023-03-25 | =C8-7 | 2023-04-01 | =edate(A7,6) |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)}
2020-10-01 | =A3 | 2020-10-08 | =A9+7 | Project management team meeting | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-01-01 | =edate(A9,3) | 2021-01-08 | =A10+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-04-01 | =edate(A10,3) | 2021-04-08 | =A11+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-07-01 | =edate(A11,3) | 2021-07-08 | =A12+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-10-01 | =edate(A12,3) | 2021-10-08 | =A13+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-01-01 | =edate(A13,3) | 2022-01-08 | =A14+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-04-01 | =edate(A14,3) | 2022-04-08 | =A15+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-07-01 | =edate(A15,3) | 2022-07-08 | =A16+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-10-01 | =edate(A16,3) | 2022-10-08 | =A17+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2023-01-01 | =edate(A17,3) | 2023-01-08 | =A18+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2023-03-25 | =C19-7 | 2023-04-01 | =edate(A18,3) |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2020-10-01 | =A3 | 2020-10-08 | =A20+7 | Independent advisory board meeting | A |  | Oversight (\textbf{Dr.\ Chrisholm}, \textbf{Steele}, \textbf{Chambers}, \textbf{Dr.\ Ibsen})
2021-04-01 | =edate(A20,6) | 2021-04-08 | =A21+7 |  | A |  | Oversight (\textbf{Dr.\ Chrisholm}, \textbf{Steele}, \textbf{Chambers}, \textbf{Dr.\ Ibsen})
2021-10-01 | =edate(A21,6) | 2021-10-08 | =A22+7 |  | A |  | Oversight (\textbf{Dr.\ Chrisholm}, \textbf{Steele}, \textbf{Chambers}, \textbf{Dr.\ Ibsen})
2022-04-01 | =edate(A22,6) | 2022-04-08 | =A23+7 |  | A |  | Oversight (\textbf{Dr.\ Chrisholm}, \textbf{Steele}, \textbf{Chambers}, \textbf{Dr.\ Ibsen})
2022-10-01 | =edate(A23,6) | 2022-10-08 | =A24+7 |  | A |  | Oversight (\textbf{Dr.\ Chrisholm}, \textbf{Steele}, \textbf{Chambers}, \textbf{Dr.\ Ibsen})
2023-03-25 | =C25-7 | 2023-04-01 | =edate(A24,6) |  | A |  | Oversight (\textbf{Dr.\ Chrisholm}, \textbf{Steele}, \textbf{Chambers}, \textbf{Dr.\ Ibsen})
2020-10-01 | =A3 | 2020-10-08 | =A26+7 | Intellectual property panel meeting | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-01-01 | =edate(A26,3) | 2021-01-08 | =A27+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-04-01 | =edate(A27,3) | 2021-04-08 | =A28+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-07-01 | =edate(A28,3) | 2021-07-08 | =A29+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-10-01 | =edate(A29,3) | 2021-10-08 | =A30+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-01-01 | =edate(A30,3) | 2022-01-08 | =A31+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-04-01 | =edate(A31,3) | 2022-04-08 | =A32+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-07-01 | =edate(A32,3) | 2022-07-08 | =A33+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-10-01 | =edate(A33,3) | 2022-10-08 | =A34+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2023-01-01 | =edate(A34,3) | 2023-01-08 | =A35+7 |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2023-03-25 | =C36-7 | 2023-04-01 | =edate(A35,3) |  | A |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
| <> |  | <> | \textbf{Steakholder involvement: IVD design \& TDM process}
2020-11-05 | =A89+21 | 2020-11-12 | =A38+7 | YPAGs (patients): prototype designs \& testing procedures | B | GOSH | GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
2021-03-08 | =C39-7 | 2021-03-15 | =C95 |  | B | North England | Newcastle Hosp., \textbf{Neil Davidson (ND)}, \emph{YPAG North England lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
2021-10-18 | =C40-7 | 2021-10-25 | =A90 |  | B | GOSH | GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
2022-02-28 | =C100 | 2022-03-07 | =A41+7 | YPAGs (patients): patient information resources co-creation | B | GOSH | GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
2022-07-25 | =A121 | 2022-08-01 | =A42+7 |  | B | North England | Newcastle Hosp., \textbf{Neil Davidson (ND)}, \emph{YPAG North England lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
2022-11-01 | =edate(A71,-1) | 2022-11-08 | =A43+7 |  | B | GOSH | GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
2020-10-01 | =A3 | 2020-10-08 | =A44+7 | PORT (parent/guardian): device \& clinical process | B |  | PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead}
2021-04-01 | =edate(A44,6) | 2021-04-08 | =A45+7 |  | B |  | PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead}
2021-10-01 | =edate(A45,6) | 2021-10-08 | =A46+7 |  | B |  | PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead}
2022-04-01 | =edate(A46,6) | 2022-04-08 | =A47+7 |  | B |  | PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead}
2022-10-01 | =edate(A47,6) | 2022-10-08 | =A48+7 |  | B |  | PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead}
2023-03-25 | =C49-7 | 2023-04-01 | =edate(A48,6) |  | B |  | PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead}
2021-10-01 | <> | 2021-11-01 | =edate(A50,1) | Public festival outreach: quantification of complex liquids | B |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead} | After informed iteration and automation complete Make this an annotation n Peditric Oncology Network meeting bar?
2022-10-01 | <> | 2022-11-01 | =edate(A51,1) |  | B |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
2020-12-01 | <> | 2020-12-08 | =A52+7 | Nurses \& doctors focus groups (ward/site visits) | B | Site A | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)}
2021-03-01 | =edate(A52,3) | 2021-03-08 | =edate(C52,3) |  | B | Site B | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)}
2021-06-01 | =edate(A53,3) | 2021-06-08 | =edate(C53,3) |  | B | Site C | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)}
2021-10-01 | <> | 2021-10-08 | =A55+7 |  | B | Site D | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)}
2021-12-01 | =edate(A55,2) | 2021-12-08 | =edate(C55,2) |  | B | Site E | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)}
2022-02-01 | =edate(A56,2) | 2022-02-08 | =edate(C56,2) |  | B | Site F | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)}
2020-10-22 | =A89+7 | 2020-10-29 | =A58+7 | Clinician / research nurse consultations (1-to-1s) | B | C | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2020-12-22 | =A91+7 | 2020-12-29 | =A59+7 |  | B | P | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2021-01-22 | =A93+7 | 2021-01-29 | =A60+7 |  | B | M | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2021-02-22 | =A95+7 | 2021-03-01 | =A61+7 |  | B | A | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2021-03-22 | =A97+7 | 2021-03-29 | =A62+7 |  | B | G | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2021-05-22 | =A99+7 | 2021-05-29 | =A63+7 |  | B | Q | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2021-11-01 | =A90+7 | 2021-11-08 | =A64+7 |  | B |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2021-11-22 | =A92+7 | 2021-11-29 | =A65+7 |  | B |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2021-12-13 | =A94+7 | 2021-12-20 | =A66+7 |  | B |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2022-01-03 | =A96+7 | 2022-01-10 | =A67+7 |  | B |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2022-01-24 | =A98+7 | 2022-01-31 | =A68+7 |  | B |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2022-02-14 | =A100+7 | 2022-02-21 | =A69+7 |  | B |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)};BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor};
2021-06-01 | <> | 2021-07-01 | =edate(A70,1) | Childhood Cancer Research Nurses Group symposia | B | TDM clin.\ best prac. | Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner} | Make this an annotation n Peditric Oncology Network meeting bar?
2022-12-01 | =edate(A70,18) | 2023-01-01 | =edate(A71,1) |  | B | IVD workflow int. | Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
| <> |  | <> | \textbf{Device regulation}
2020-10-01 | <> | 2020-10-15 | =A73+14 | Quality Management System (QMS) management reviews | C | Initialisation | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};
2021-01-01 | =edate(A75,-2) | 2021-01-08 | =A74+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-03-01 | =edate(A81,-2) | 2021-03-08 | =A75+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-08-01 | =edate(A85,1) | 2021-08-08 | =A76+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-09-01 | =edate(A76,1) | 2021-09-08 | =A77+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-01-18 | =edate(A86,3) | 2022-01-25 | =A78+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-06-18 | =edate(A78,5) | 2022-06-25 | =A79+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-12-18 | =edate(A79,6) | 2022-12-25 | =A80+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-05-01 | =edate(A85,-2) | 2021-05-08 | =A81+7 | Internal audits | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-10-01 | =edate(A77,1) | 2021-10-08 | =A82+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-04-18 | =edate(A86,6) | 2022-04-25 | =A83+7 |  | C |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2023-01-01 | =edate(C84,-3) | 2023-04-01 | <> |  | C | Tech. file compilation | Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead}
2021-07-01 | <> | 2021-07-08 | =A85+7 | External audits by Notified Body (BSI; ISO 13485) | C | Documentation | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2021-10-18 | =edate(A82,1)-14 | 2021-10-25 | =A86+7 |  | C | Certification | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-10-18 | =edate(A86,12) | 2022-10-25 | =A87+7 |  | C | Surveillance | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.};UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
| <> |  | <> | \textbf{IVD components: device prototyping}
2020-10-15 | =A73+14 | 2020-12-15 | =EDATE(A89,2) | Cartridge consumable (C) | D | C | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2021-10-25 | =C86 | 2021-11-15 | =A90+21 |  | D | C | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2020-12-15 | =C89 | 2021-01-15 | =EDATE(A91,1.5) | Biological matrix processing hub (P) | D | P | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2021-11-15 | =C90 | 2021-12-06 | =A92+21 |  | D | P | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2021-01-15 | =C91 | 2021-02-15 | =EDATE(A93,1.5) | Optical/measurement hub (M) | D | M | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2021-12-06 | =C92 | 2021-12-27 | =A94+21 |  | D | M | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2021-02-15 | =C93 | 2021-03-15 | =EDATE(A95,1.5) | Automated desktop unit (A) | D | A | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Sombra, \textbf{Yuriy Nakonechnyy}, emph{UI software dev.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2021-12-27 | =C94 | 2022-01-17 | =A96+21 |  | D | A | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Sombra, \textbf{Yuriy Nakonechnyy}, emph{UI software dev.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2021-03-15 | =C95 | 2021-05-15 | =EDATE(A97,2) | Graphical user interface (G) | D | G | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Sombra, \textbf{Yuriy Nakonechnyy}, emph{UI software dev.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2022-01-17 | =C96 | 2022-02-07 | =A98+21 |  | D | G | Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.};Sombra, \textbf{Yuriy Nakonechnyy}, emph{UI software dev.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2021-05-15 | =C97 | 2021-06-15 | =EDATE(A99,1.5) | Quantification algorithm (Q) | D | Q | Sombra, \textbf{Yuriy Nakonechnyy}, emph{UI software dev.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2022-02-07 | =C98 | 2022-02-28 | =A100+21 |  | D | Q | Sombra, \textbf{Yuriy Nakonechnyy}, emph{UI software dev.};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};
2020-12-15 | =C89 | 2021-06-15 | =C99 | Manufacture and assembly | D | Semi-automated IVD
2021-11-15 | =C90 | 2022-02-28 | =C100 |  | D | Fully-automated IVD
| <> |  | <> | \textbf{IVD analytical validation: internal quality assessment (IQA)} | E
2021-06-15 | =C101 | 2021-06-29 | =A104+14 | Range and response: calib., LLOQ \& ULOQ | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-02-28 | =C100 | 2022-03-21 | =A105+21 |  | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2021-06-29 | =C104 | 2021-07-13 | =A106+14 | Accuracy and precision: QCs within-run \& between-run | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-03-21 | =C105 | 2022-04-11 | =A107+21 |  | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2021-07-13 | =C106 | 2021-07-27 | =A108+14 | Selectivity: blank matrices, response at rf. | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-04-11 | =C107 | 2022-05-02 | =A109+21 |  | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2021-07-27 | =C108 | 2021-08-10 | =A110+14 | Matrix effects: spiked matrices, response interference | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-05-02 | =C109 | 2022-05-23 | =A111+21 |  | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2021-08-10 | =C110 | 2021-08-24 | =A112+14 | Specificity: metabolites \& concomitant med. | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-05-23 | =C111 | 2022-06-13 | =A113+21 |  | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2021-08-24 | =C112 | 2021-09-07 | =A114+14 | Stability: degradation (procesing \& storage) | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-06-13 | =C113 | 2022-07-04 | =A115+21 |  | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2021-09-07 | =C114 | 2021-09-21 | =A116+14 | Carry over: blanks alongside calibration curve | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-07-04 | =C115 | 2022-07-25 | =A117+21 |  | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2021-09-21 | =C116 | 2021-10-05 | =A118+14 | Dilution integrity: replicates for acc.\ \& precision | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-07-25 | =C117 | 2022-08-15 | =A119+21 |  | E |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
| <> |  | <> | \textbf{IVD analytical validation: external quality assessment (EQA)}
2022-07-25 | =C121-21 | 2022-08-15 | =C119 | Blind sample preparation | F |  | Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.}; QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-08-15 | =C119 | 2022-08-22 | =A122+7 | Parallel sample challenges: Doxorubicin (DOX) | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-09-12 | =C140 | 2022-09-19 | =A123+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-10-10 | =C141 | 2022-10-17 | =A124+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-11-07 | =C142 | 2022-11-14 | =A125+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-12-05 | =C143 | 2022-12-12 | =A126+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2023-01-02 | =C144 | 2023-01-09 | =A127+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-08-22 | =C122 | 2022-08-29 | =A128+7 | Parallel sample challenges: Daunorubicin (DAU) | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-09-19 | =C123 | 2022-09-26 | =A129+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-10-17 | =C124 | 2022-10-24 | =A130+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-11-14 | =C125 | 2022-11-21 | =A131+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-12-12 | =C126 | 2022-12-19 | =A132+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2023-01-09 | =C127 | 2023-01-16 | =A133+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-08-29 | =C128 | 2022-09-05 | =A134+7 | Parallel sample challenges: Epirubicin (EPI) | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-09-26 | =C129 | 2022-10-03 | =A135+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-10-24 | =C130 | 2022-10-31 | =A136+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-11-21 | =C131 | 2022-11-28 | =A137+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-12-19 | =C132 | 2022-12-26 | =A138+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2023-01-16 | =C133 | 2023-01-23 | =A139+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-09-05 | =C134 | 2022-09-12 | =A140+7 | Parallel sample challenges: Idarubicin (IDA) | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-10-03 | =C135 | 2022-10-10 | =A141+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-10-31 | =C136 | 2022-11-07 | =A142+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-11-28 | =C137 | 2022-12-05 | =A143+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2022-12-26 | =C138 | 2023-01-02 | =A144+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
2023-01-23 | =C139 | 2023-01-30 | =A145+7 |  | F |  | Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.};QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
| <> |  | <> | \textbf{Business development and healthcare integration} |  |  |  | Put this section closer to PPI section?
2020-10-01 | <> | 2020-12-01 | =edate(A147,2) | Market review and analysis | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};
2020-12-01 | =C147 | 2021-05-01 | =A149 | Pharmaceutical industry engagement | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};
2021-05-01 | =edate(C149,-3) | 2021-08-01 | <> | Freedom to operate re-evalutation | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};
2021-08-01 | =C149 | 2021-10-01 | =A151 | Industrial engagement (downstream partners) | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};
2021-10-01 | =edate(C151,-6) | 2022-04-01 | <> | Health economic analysis | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};NIHR London IVD Co-operative, \textbf{Dr.\ M.\ Ng (MIC)}, \emph{Health.\ econ.}
2022-03-01 | <> | 2022-06-01 | =edate(A152,3) | IP review and patent applications | G |  | UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead};Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead};UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
2022-04-01 | =C151 | 2022-07-01 | =edate(A153,3) | Pricing consultation | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};NIHR London IVD Co-operative, \textbf{Dr.\ M.\ Ng (MIC)}, \emph{Health.\ econ.};NIHR London IVD Co-operative, \textbf{Dr.\ M.\ Ng (MIC)}, \emph{Health.\ econ.}
2022-07-01 | =edate(C154,-3) | 2022-10-01 | =edate(A156,2) | Meetings and design of live trials (localised pilots) | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};
2022-06-01 | =C152 | 2022-09-01 | =edate(A155,3) | Business case development | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};
2022-08-01 | =edate(C156,-8) | 2023-04-01 | <> | Follow-on grant applications and finance raise | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};
2022-08-01 | =A156 | 2022-12-01 | =edate(A157,4) | Engagement with NICE Health Tech assessment | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};NIHR London IVD Co-operative, \textbf{Dr.\ M.\ Ng (MIC)}, \emph{Health.\ econ.}
2023-01-01 | =edate(C158,-3) | 2023-04-01 | <> | Commissioner engagement | G |  | UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead};
Formulas:
End = [Start]+7
End = edate([Start, row above],6)
Start = edate([Start, row above],6)
Start = [End]-7

## Sheet3
Vesynta, \textbf{Dr.\ A.\ Taylor (AT)}, \emph{Innovation and design lead}
Sombra, \textbf{Yuriy Nakonechnyy}, emph{UI software dev.}
Pix Medical, \textbf{S. C. Mussalian}, \emph{Functional eng. \& manufacture.}
UCL, \textbf{Dr.\ S.\ Guldin (SG)}, \emph{Project lead}
UCL, \textbf{Dr.\ J.\ Suthar (JS)}, \emph{Prog. man.\ \& bus.\ dev.\ lead}
PORT, \textbf{N.\ Ranasinghe (NR)}, \emph{PPI rep.\ (parents)}
Oxford Medical Devices, \textbf{Dr.\ M.\ Gould (MG)}, \emph{Regulatory cons.}
QServe, \textbf{Sue Spencer}, \emph{IVDR compliance}
Oversight (\textbf{Dr.\ Chrisholm}, \textbf{Steele}, \textbf{Chambers}, \textbf{Dr.\ Ibsen})
Newcastle Uni., \textbf{Prof.\ G.\ Veal}, \emph{Clinical pharmacology lead}
Newcastle Uni., \textbf{Dr.\ S.\ Barnett (SB)}, \emph{Val.\ \& EQA res.\ ass.}
NIHR London IVD Co-operative, \textbf{Dr.\ M.\ Ng (MIC)}, \emph{Health.\ econ.}
GOSH, \textbf{D.\ Leyden (DL)}, \emph{YPAG GOSH lead}
GOSH, \textbf{A. Bedi (AB)}, \emph{PPI rep.\ (senior research nurse)}
CreativPro, \textbf{F.\ Irigaray (FI)}, \emph{Visual arts practitioner}
BCH, \textbf{Prof.\ P.\ Kearns (PPK)}, \emph{Chief clinical advisor}
Newcastle Hosp., \textbf{Neil Davidson (ND)}, \emph{YPAG North England lead}